## README
Team 5 — AI Adoption Index: Shared Tracker
This spreadsheet is the SOURCE OF TRUTH for who owns what and by when (team contract).
GitHub Issues/board hold engineering detail underneath it: https://github.com/MehulPardeshi/ai-adoption-index/blob/main/docs/TASK_TRACKER.md
Rules
1. Every task has ONE owner (others go in 'Support'). Owner = TBD until agreed by majority vote.
2. Update Status yourself: To Do / In Progress / Blocked / Done.
3. If a task has a GitHub issue, paste its link in 'GitHub issue'.
4. Missed deadline → follow conflict-resolution steps (memory/02-team-norms.md): note it in 'Notes', due next sprint.
5. Don't rename or reorder columns — the repo docs reference this format.
6. Decisions (roles, tools, dates) also go in memory/09-decisions-log.md in the repo.

## Tasks
ID | Area | Task | Owner | Support | Status | Start | Due | GitHub issue | Notes
T01 | Setup | Invite teammates to GitHub repo + kanban board | Mehul |  | To Do | 2026-09-28 | 2026-09-29 |  | Needs everyone's GitHub username
T02 | Setup | Share this tracker (Google Sheet) with the team; link logged in repo | Mehul |  | To Do | 2026-09-28 | 2026-09-28 |  | Link goes in docs/TASK_TRACKER.md + memory/09
T03 | Setup | Schedule & run virtual setup call (clone repo on every laptop, walk through structure) | Mehul | All | To Do | 2026-09-28 | 2026-09-30
T04 | Setup | Each member: clone repo, run onboarding prompt, create team/<name>.md profile (role pick, bio, client questions), open PR | All |  | To Do | 2026-09-29 | 2026-09-30 |  | One PR per person; see ONBOARDING_FOR_NON_CODERS.md
T05 | Setup | Review & merge profile PRs | Mehul |  | To Do | 2026-09-29 | 2026-09-30
T06 | Team | Majority vote on roles; log result in memory/09-decisions-log.md + Roles tab | All |  | To Do | 2026-09-30 | 2026-10-01 |  | Can be done on setup call
T07 | TP1 | Research Julie Agnew & William & Mary (course requirement before 1st client meeting); add 1–2 questions each in your profile | All |  | To Do | 2026-09-29 | 2026-09-30
T08 | TP1 | Compile ~1-page client-meeting prep doc (docs/tp1/client_meeting_prep.md) | TBD |  | To Do | 2026-09-30 | 2026-09-30 |  | TP1 submission doc #2
T09 | Client | First client requirements meeting with Julie (Thu 2–3pm) | Snehal (pending confirmation) | All | To Do | 2026-10-01 | 2026-10-01 |  | Agree progress-meeting date (late Oct/early Nov); invite Julie to final presentation
T10 | TP1 | Take meeting notes; log decisions in memory/09 | TBD |  | To Do | 2026-10-01 | 2026-10-01
T11 | TP1 | Draft project scope doc (PMI format) incl. kanban board link (docs/tp1/project_scope.md) | TBD | All review | To Do | 2026-10-01 | 2026-10-02 |  | TP1 submission doc #3
T12 | Client | Send scope doc to Julie for approval | Snehal (pending confirmation) |  | To Do | 2026-10-02 | 2026-10-02
T13 | TP1 | Submit TP1 on Canvas: signed contract + prep doc + scope doc (with board link) | TBD |  | To Do | 2026-10-02 | 2026-10-02 |  | Due Fri 5:00pm per syllabus — confirm in Canvas. No late team submissions.
T14 | Team | Fill blank contract section 4 (Expectations / Attendance) — optional | All |  | To Do
W1 | Week 1 | Source review, ethics memo, firm universe | TBD |  | To Do |  |  | https://github.com/MehulPardeshi/ai-adoption-index/issues/1 | Calendar dates TBD — log in memory/09
W2 | Week 2 | Draft taxonomy from 30–50 sample documents | TBD |  | To Do |  |  | https://github.com/MehulPardeshi/ai-adoption-index/issues/2
W3 | Week 3 | Metrics design + inter-rater reliability testing | TBD |  | To Do |  |  | https://github.com/MehulPardeshi/ai-adoption-index/issues/3
W4 | Week 4 | Backfill data collection and coding (8–12 quarters) | TBD |  | To Do |  |  | https://github.com/MehulPardeshi/ai-adoption-index/issues/4
W5 | Week 5 | Index construction and weighting experiments | TBD |  | To Do |  |  | https://github.com/MehulPardeshi/ai-adoption-index/issues/5
W6 | Week 6 | Dashboard build and final presentation | TBD |  | To Do |  |  | https://github.com/MehulPardeshi/ai-adoption-index/issues/6
C1 | Course | Course technical requirements checklist (agentic tools, skill folder, guardrails, hosted app…) | TBD |  | To Do |  | 2026-12-03 | https://github.com/MehulPardeshi/ai-adoption-index/issues/7 | TP2 due Fri 11/6 (12 pts need a working agentic component)

## Roles
Name | Andrew email | GitHub username | Proposed role | Status | Profile file
Mehul Pardeshi | mppardes@andrew.cmu.edu | MehulPardeshi | Project Manager + Responsible AI lead | Proposed — pending vote | team/mehul-pardeshi.md
Yen-Chu Chen | yenchuc2@andrew.cmu.edu
Logan Mai | loganmai@andrew.cmu.edu
Shu Pu | shup@andrew.cmu.edu
Snehal Paliwal | snehalp@andrew.cmu.edu |  | Client communication (already de facto) + ? | Pending Snehal's confirmation

## Meetings
Date | Type | Attendees | Key decisions (also log in memory/09) | Action items (add to Tasks tab)
2026-09-20 (Sun) | Internal | All | Team contract agreed (signed 9/20–9/24) | Set up tracker
2026-10-01 (Thu) | Client — Julie