Team Meeting Capture Form

Team 5 · Sun Oct 4, 2026, 8:00–9:00 pm · AI Adoption Index

Our plan in one minute - TP1 is done ✅. Next big deadline: TP2 on Fri Nov 6 (a progress report, an early working demo, and a meeting with Julie). - This week (Oct 5–9) is finals and next week (Oct 12–16) is fall break, so no project work is expected. - We restart Sun Oct 18, which gives us about 3 weeks (Oct 18–Nov 6). - Plan: do a small test run on 5–6 big companies ("proof of concept"), show it to Julie around Oct 29–30, then write TP2. - Tonight's goal: decide the details, so everyone knows exactly what to start on Oct 18.

How to use this form: fill in "Our answer" during the meeting. Blank = not decided yet. Afterwards, send this form plus the Gemini transcript to Claude, which updates GitHub for everyone.

# Basics

| # | Question | Our answer |
| --- | --- | --- |
| B1 | Who attended? Who couldn't make it? | All Teammates |
| B2 | Is the Gemini note-taker on? Who will send tonight's notes to Claude afterwards? Why: So GitHub gets updated with what we decided, and everyone's AI tool knows the plan. | Yes. ZoomAI |

# 1. Update from Julie

| # | Question | Our answer |
| --- | --- | --- |
| 1a | Did Julie reply to our scope document? Any comments? Why: If she wants changes, we should know before we start working. | Snehal is yet to send the email to Julie |
| 1b | Did Julie send the research paper she promised? Paste the link. Why: We're reading it before deciding how to measure AI adoption. | Julie is yet to send the paper |

# 2. New dates

The scope we sent Julie says we'd show her first results in mid-October. We're away until Oct 18, so we need new dates and should tell her.

| # | Question | Our answer |
| --- | --- | --- |
| 2a | When can we realistically have our first results ready? (Suggestion: Thurs Oct 29.) Why: This is our target for the test run on 5–6 companies. | Thursday, October 29 from 1-2 PM |
| 2b | When should we meet Julie to show them? (Suggestion: Thu Oct 29 or Fri Oct 30.) Why: Julie prefers Thursdays/Fridays, and TP2 (due Nov 6) asks us to have this meeting first. | Thursday, October 29 N/A |
| 2c | Who emails Julie about the new dates, and by when? Why: Snehal is our client lead; Julie asked us to follow up if there's no reply in 24 hours. | Snehal |
| 2d | Is anyone busy or away between Oct 18 and Nov 6? Why: So we can plan work around it. | No |

# 3. Our test run (the "proof of concept")

A proof of concept = a small trial on a few companies to check our idea works, before we expand. Julie asked for 5–6 big financial companies.

| # | Question | Our answer |
| --- | --- | --- |
| 3a | Which 5–6 companies? (e.g., JPMorgan, Bank of America, Wells Fargo, Citigroup, Goldman Sachs, Morgan Stanley; or include a retirement company.) Why: Julie suggested starting with big public banks. Note: Fidelity and Vanguard are private, so they have no SEC reports. | - JP Morgan - Julie's own example; biggest U.S. bank with heavy public AI disclosure - Bank of America - Major public bank - Capital One - Major public bank (Branded tech forward) - Wells Fargo - Major public bank - Charles Schwab - Wealth management and retirement accounts; links to the book chapter on AI in retirement - Principal Financial Group - Major retirement plan provider (recordkeeper) that files with the SEC |
| 3b | How many years back do we look? (Suggestion: 2–3 years, not 5.) Why: More years means more work. We have ~2 working weeks, and the original brief asks for at least 2 years (8 quarters). | 2024-2026 |
| 3c | Which documents do we start with? (Suggestion: annual and quarterly reports (10-K, 10-Q) from the SEC first.) Why: SEC reports are free and easy to download. Earnings-call transcripts are richer but harder to collect, so maybe add them later. | Data Sources - 10-K, 10-Q (SEC) (Shu) - GitHub (Shu) - Earning calls (yen) - LinkedIn (yen) |
| 3d | What exactly will we show Julie at the end? (e.g., a simple chart of how often each company talks about AI, and for what purposes.) Why: Agreeing on this now keeps us from over-building. | - Company View - Detailed click in - Categories for Index - Investment in AI - AI integration in final product - Jobs related to AI |

# 4. Who does what after the break

Owners already agreed are filled in. Confirm them and add a due date.

| Task (in plain words) | Why it matters | Owner | Due |
| --- | --- | --- | --- |
| Write our rules for collecting data responsibly (the "ethics memo") | 10% of the grade; must be done before we download lots of data | Logan |  |
| Download the reports for our chosen companies | Raw material for everything else | Yen-Chu, Shu |  |
| Read sample reports and list the ways companies use AI (first categories) | This becomes our "taxonomy" (20% of the grade) | Yen-Chu, Shu |  |
| Plan how we'll check our results are correct | Required by the course; makes our numbers trustworthy | Mehul |  |
| Build the first working version of the AI agent | Biggest single item in TP2 (12 of 50 points) | Shu |  |
| Sketch the dashboard (what Julie will see), mock up functionality | Shows Julie the direction early | Snehal |  |
| Look at existing AI trackers and what they measure | Shows what's new about ours | Logan, Snehal |  |
| Set up the meeting with Julie | Required before TP2 | Snehal |  |
| Write the TP2 progress report (1–3 pages) + board screenshot | Due Fri Nov 6 |  |  |

# 5. Anything during the break? (optional)

| # | Question | Our answer |
| --- | --- | --- |
| 5a | Does anyone want to do something small during the break (e.g., read the AI paper)? Totally optional. Why: Nothing is required; just note any volunteers. | Before meeting Sunday October 18 review Julie’s paper, GitHub link, and be prepared to talk about your action plan after break! :) ALSO research how the AI engineering will happen. |

# 6. Tools

| # | Question | Our answer |
| --- | --- | --- |
| 6a | What do we build the dashboard with? (Suggestion: Streamlit, a free Python tool that's easy to put online.) Why: The course requires the final app to be hosted online. | Streamlit, Vercel to deploy |
| 6b | Which AI model do we use? It must be free (we have no budget). Why: The course requires us to use an AI model in the solution. | Research, come back Oct. 18 |
| 6c | Shu: any first ideas for the AI agent's "tools" (small functions the agent can call, e.g., "fetch a company's reports")? Why: The course requires at least 5 custom tools. | Research, come back Oct. 18 |

# 7. Loose ends

| # | Question | Our answer |
| --- | --- | --- |
| 7a | Who asks Dr. Chung which parts of the original assignment still count for our grade? Why: Julie said simple methods are fine, but the original brief has stricter requirements. We should know which ones we're graded on. | Confirm with Dr. Chung during OH post finalized scoping with Julie. |
| 7b | Is Hengkai Zheng our TA? (The syllabus lists him for another section.) Why: So we know who to go to for help. | Yes, our advisor for this project |
| 7c | Do we want to coordinate with Team 15, or work fully separately? Why: Julie wants separate updates from each team. | Work separately from now out → different streams of work |
| 7d | Our contract left "what doing your share means" blank. Fill it in, or skip? Why: Optional; helps if workload issues come up later. | Filled this out before TP1 deadline |
| 7e | When is our next meeting? (Suggestion: Sun Oct 18, 8–9 pm.) | Sunday, Oct. 18 8-9 PM |

# 8. Wrap-up

| Action item | Owner | Due | Done? |
| --- | --- | --- | --- |
| Research part 6 | All | Oct 18 |  |
| Send Julie follow up | Snehal | Oct 5 |  |
| Review Julie’s paper, github, and other resources she provides | All | Oct 18 |  |

| # | Question | Our answer |
| --- | --- | --- |
| 8a | What did we decide tonight? (2–3 lines) | Part 3 |
| 8b | Anything else Claude should update? | No |